## 工作表1
sprint owner: | yingwenz
Feature:Draw
task | description | date | time(h) | owner
drawer page display | create a game(including keyword),render the drawer's page, and establish socket connection | 10.27.-10.30 | 5 | tianqiz
implement canvas | drawer can draw in the canvas and display the content simultaneously | 10.27.-10.30 | 3 | tianqiz
transmit and store canvas | send canvas content to server and store the current canvas of the game | 10.31.-11.2. | 4 | tianqiz
display guesser's guess | if guess correctly, alert correct message, if not, display the wrong guess | 10.31.-11.2. | 3 | tianqiz
Feature:Guess
task | description | date | time(h) | owner
guesser page display | render the guesser's page and establish socket connection | 10.27.-10.30 | 5 | yingwenz
display canvas | server sends the canvas to guesser and the canvas is displayed on guesser's page | 10.27.-10.30 | 3 | yingwenz
submit guess | sumbit the guess keyword to the server | 10.31.-11.2. | 2 | yingwenz
display result | if guess correctly, alert correct message, if not, alert error message | 10.31.-11.2. | 3 | yingwenz
Feature:Timer display
task | description | date | time(h) | owner
timer generate | server sends updated timer to two clients every second | 11.3.-11.4 | 3 | tianqiz
Feature:End game | description | date | time(h) | owner
end the game based on guess | end the game if the guess is correct | 11.3.-11.4 | 2 | yingwenz
end the game based on time | end the game if time runs out | 11.3.-11.4 | 2 | yingwenz