## 工作表1
sprint owner: | tianqiz
Feature:add player model
task | description | date | time(h) | owner
player register and login | player can register a new account and login the account | 11.9-11.10. | 5 | yingwenz tianqiz
edit profile | player can edit their profile | 11.15-11.16 | 3 | tianqiz
display player score | player can see their score on profile page | 11.15-11.16 | 2 | tianqiz
Feature:room functionality
task | description | date | time(h) | owner
create room | player can create a new game room | 11.14-11.15 | 4 | tianqiz
search room | player can search room by room information | 11.14-11.15 | 6 | yingwenz
Feature: game validation
task | description | date | time(h) | owner
validate the player role | validate that in one game there only consist of one guesser and one drawer | 11.11-11.13 | 5 | tianqiz
validate the number of player in one game | validate that only two players can join one room | 11.11-11.13 | 5 | yingwenz
Feature: game score
task | description | date | time(h) | owner
score the player if game success | add players' score if game success | 11.17 | 1 | yingwenz