## 工作表1
sprint owner: | yingwenz
Feature:deploy
task | description | date | time(h) | owner
deploy | deploy using AWS and Nginx and MySQL(not decided yet) | 11.22-11-24 | 10 | tianqiz, yingwenz
Feature:restore game
task | description | date | time(h) | owner
save game data | when a player disconnect by accident, game content is saved | 11.26-11.27 | 6 | tianqiz
render game data | when the player reconnect, render the page with correct data | 11.26-11.27 | 6 | yingwenz
Feature: player ranking
task | description | date | time(h) | owner
create rank page | render first 50th players' rank and personal rank | 11.25 | 4 | yingwenz
display personal rank | Display player rank on home page | 11.25 | 2 | tianqiz
Feature: bug fix
task | description | date | time(h) | owner
bug fix | test corner cases, find potential bugs and fix them. | 11.28-12.1 | 10 | yingwenz, tianqiz
UI modification | modify the UI so that user can see instructions clearly | 11.28-12.1 | 2 | tianqiz